## Deliverables
Doña Fuego × Johannes — Deliverables Tracker
Engagement: 4 × 1hr sessions/month (Jun–Sep 2026) + WhatsApp working group · Product: Doña Fuego Tequila RTD — 4 SKUs (Margarita, Spicy Margarita, Paloma, Non-alc Margarita), 250ml / 7% ABV, R169 per 4-pack, 6 × 4-packs per case · First Checkers PO R2.7m (~9,000L / 1,500 cases / 36,000 units per SKU; 3 cases per store) · 12-mo exclusivity with Checkers + Checkers Liquor + 60/60 · Launch July 2026, consumer campaign live September 2026 · Updated 11 Jun 2026
# | Deliverable | Description / Scope | Owner | Support / Resources | Target Date | Status | % Done | Notes | Link | Budget (R)
1 | Target audience & cooler-box occasion | Lead audience confirmed = existing tequila drinkers (blue space, no big-brand RTD tequila competition). Anchor persona "Sannie from Sea Point" (Sweat 1000, walks the prom, wine farms on weekends, late 20s–late 30s, cosmopolitan). Primary occasion locked = SHARE OF COOLER BOX (braai, boat, picnic, holiday). Premise: nobody wants to bring all the margarita kit, and bringing wine to every braai is boring. | Johannes + Danielle | Danielle (customer insight); ChatGPT/Claude for audience research | 2026-06-19 | Done | 60% | Confirmed in 11 Jun marketing session — cooler-box framing landed. This now anchors all positioning and campaign work. | https://lit.africa/ | 0
2 | Brand positioning & "Anti-Wine Club" messaging | Lock messaging house around "the drink you bring when everyone else brings wine" / Anti-Wine Club. Key angles: real tequila (no BS, founder-distiller story), premium RTD at R169/4-pack vs Brutal Fruit/Bernini, 4-SKU range with non-alc as differentiator, Margarita/Paloma serve naming (not 'tequila') to defuse "I don't drink tequila" objection. | Johannes | Danielle (input/sign-off); copywriting support TBC | 2026-06-30 | In Progress | 20% | Tagline direction emerging. Must justify R169/4-pack vs cheaper RTDs at shelf. Lean on real-tequila + cooler-box convenience + non-alc. |  | 5000
3 | Cooler-box launch campaign (live Sept) | Integrated September campaign built around the cooler-box-share idea. Tactics: (a) cooler-brand partnership — Plan A Field Bar (buy ~30 mini bars, cans fit perfectly), Plan B Yeti / Igloo / Coleman / Freedom of Movement; partner amplifies via emailer + social to drive to Checkers; (b) Surprise-and-delight: first 20 people to WhatsApp their braai address get a cooler box of margaritas dropped via Uber, photographer captures, content fuels the campaign video; (c) #DoñaFuego photo competition into the audience file; (d) optional Yeti stunt = "longest margarita pour of all time" (30 days in a Yeti). | Johannes + Danielle | Field Bar head of marketing & partnerships (LinkedIn intro), backup cooler brands, designer, photographer, Uber delivery | 2026-09-01 | In Progress | 10% | Moved from July to SEPTEMBER — July/Aug = trade execution + shelf hygiene; September = consumer drop. This week: Johannes connects with Field Bar head of marketing on LinkedIn; Danielle drafts the partnership pitch email. NO price discounting — invest in tastings/campaign instead. | https://fieldbar.co.za/collections/mini-bar | 130000
4 | Trade marketing — platinum stores + sell-out dashboard | Get a weekly auto sales-out report per store from the Checkers buyer (non-negotiable — needed to see what's moving and catch stores where stock is sitting in the back not on shelf). Identify top 20–50 "platinum" stores nationally and concentrate ~80% of marketing/tastings/giveaways on them. Use existing reps (Swift / National) as eyes-on for problem stores; Checkers' internal merchandising handles the rest. | Johannes + Danielle | Checkers buyer (auto report + sign-off), Swift / National reps, simple sell-out dashboard | 2026-07-18 | In Progress | 5% | Every Checkers store = a billboard. Action: Danielle asks buyer for weekly auto sales-out report. Johannes builds light dashboard once data flowing. |  | 5000
5 | "1,000 Top Fans" audience file & content engine | Living Claude working file capturing mentions, photos, competition entries, top customers from day one. Foundation for content amplification and the September campaign. Cooler-box-drop event photography + Field Bar partnership content feed straight into this. | Johannes | Claude working file, social listening, photographer outputs, competition entries | 2026-07-25 | Not Started | 0% | Stand up before launch so day-one mentions/photos are captured. Replaces the old "~80 PR pieces" target — trade marketing + Sept campaign is the lead channel, not traditional PR. | https://circle.so/ | 30000
6 | Pitch deck & data room (HTML / Claude-built) | Raise-ready pack for the BRAND only — not the bulk arm. Structure: separate SBB holding the trademark with a supply agreement back to the distillery. Vision-led ~10-page interactive HTML deck (not a 30-slide PDF) + live FAQ that grows as investors ask questions. Target valuation ~R20m pre-launch on the blue-sky story before actuals come in. Pair with cash flow model (#7). | Johannes | Danielle (raw inputs, financials, vision), Claude (build), legal (entity spin-out + supply agreement) | 2026-07-24 | In Progress | 10% | Johannes building this/next week (incl. from Mozambique). Danielle to send raw inputs + a view on what she wants from a strategic partner. Raise on cash flow story, not revenue — actuals dilute the valuation multiple. |  | 15000
7 | Cash flow model | Plug Danielle's raw inputs (bulk-tequila prepayments, Tiny Keg 50/50 terms, R600k excise, Checkers 60-day cash cycle, allocation pre-payments from Patch/Cheeky/Heinos, first R2.7m PO + replenishment) into Johannes's cash flow template. 12-month view. Supports the raise conversation AND the ABSA overdraft / West Peak Capital / White Rock facility decisions. | Johannes | Danielle (raw inputs); Johannes's cash flow template | 2026-06-27 | Not Started | 0% | Replaces old "Strategic partner shortlist" line — the raise is now the primary route, partner shortlist becomes a sub-output of the deck. Financing is in Danielle's hands (ABSA overdraft = base case; West Peak / White Rock ~R1.5m facility as backup), Johannes only on the model. |  | 0
8 | Sounding board / coaching (ongoing) | 4 × 1hr structured sessions per month + ad-hoc via WhatsApp working group. Independent space to think out loud and stay accountable on marketing focus while Danielle runs the rest of the distillery business. | Johannes | WhatsApp working group (to set up) | Ongoing | In Progress | 15% | Sessions done: 9 Jun intro, 11 Jun marketing session. Next session ~20 Jun. WhatsApp group to be set up for ad-hoc questions and link sharing. |  | 0
[6 empty] | Overall | 15% |  |  | 185000
Note on J5: Johannes Le Roux: LIT Africa — SA influencer / creator marketing platform. Audience research + amplification for the Sept campaign.
Note on K5: Johannes Le Roux: In scope of engagement — no external spend.
Note on K6: Johannes Le Roux: Light copywriter pass on the messaging house (est.).
Note on J7: Johannes Le Roux: Field Bar mini bars — cans fit perfectly. Plan A partner for the cooler-box campaign.
Note on K7: Updated: 30 mini Field Bars × R1,799 = R53,970 + 20 Uber cooler-box drops (~R30k) + photographer (~R20k) + tastings & in-store activation (~R20k) + design assets (~R5k). ~R130k total. Negotiate Field Bar partnership rate — likely better than retail.
Note on K8: Johannes Le Roux: Light dashboard build; sales-out feed from buyer is free.
Note on J9: Johannes Le Roux: Circle.so — community platform option for hosting the 1,000 Top Fans community.
Note on K9: Johannes Le Roux: Circle.so subscription (~R1,800/mo × 12) + LIT Africa setup + light tooling. Est.
Note on K10: Johannes Le Roux: Designer polish on HTML deck + legal review of supply agreement / SBB spin-out. Legal TBC with Danielle's existing lawyer.
Note on K11: Johannes Le Roux: In scope — Johannes template, no external spend.
Note on K12: Johannes Le Roux: Retainer covers sessions + WhatsApp.

## Resources & Skills
Resource & Skill Requirements
Who/what is needed to deliver, and where it comes from
Resource / Skill | Type | Needed For (Deliverable #) | Source | Status | Est. Cost | Notes
Marketing strategy & positioning | Skill | 1, 2, 3, 5 | Johannes (in scope) | Secured | In retainer | Core of the engagement.
Founder time & customer insight | Time | 1, 2, 3, 7 | Danielle | Secured | — | ~Weekly sessions + homework (personas, partner intros).
Cooler-brand partnership (Field Bar / Yeti / Igloo) | Partner | 3 | Approach via Johannes LinkedIn intro — Field Bar head of marketing & partnerships first; Yeti / Igloo / Coleman / Freedom of Movement as backup | Not Secured | 30 × R1,799 = R53,970 (retail) — negotiate partnership rate | Plan A Field Bar (cans fit the mini perfectly). Plan B Yeti (premium, now in SA but ~R7k). Brand amplifies via emailer + social to drive to Checkers.
Graphic designer (campaign assets) | Specialist | 3, 6 | Existing label designer or J network | Secured | TBC | Label design already strong; reuse same designer if possible.
Trade marketing & retail reps | Specialist | 4 | Swift / National (existing relationship); Checkers internal merchandising | Secured | In existing reps' scope | Replaces PR/influencer line — Sept campaign is the lead amplification channel, not traditional PR. Reps as eyes-on for problem stores; buyer's internal merch handles the rest.
Checkers sales-out data feed | Data | 4, 5 | Weekly auto report from Checkers buyer | Not Secured | — | Non-negotiable. Danielle to ask buyer. Feeds the platinum-stores dashboard and the audience file.
Cash flow modelling | Skill | 6, 7 | Johannes (template) | Secured | In retainer | Danielle sends raw inputs (bulk tequila, Tiny Keg terms, Checkers cycle, allocations). Supports raise + overdraft conversation.
Deck design | Specialist | 6 | Designer (J network) | Not Secured | TBC | Polish only — content from J + Danielle.
Legal (entity spin-out) | Specialist | 6, 7 | Danielle's existing legal | Not Secured | TBC | Standard model: build in distillery → separate entity → sell equity.
Checkers buyer relationship | Relationship | 3, 5 | Danielle (existing, strong) | Secured | — | Buyer championed product through tasting panels.
Industry / distributor network | Relationship | 7 | Johannes | Secured | — | For strategic partner shortlist.